## sow
No | Scope Of Works | Day |  |  |  |  | Status
|  | 1 | 2 | 3 | 4 | 5
Configure AWS Infra 1st Launch | [6 empty] | done
2 | Create New AWS VPC TEDS | [5 empty] | done
3 | Create New 2 Public Subnet (Multi-AZ) | [5 empty] | done
4 | Create New Private Subnet (Multi-AZ) | [5 empty] | done
5 | Create New NACL & Route Table | [5 empty] | done
6 | Create AWS EFS | [5 empty] | on prgress
7 | Create Application Load Balancer | [5 empty] | done
8 | Configure Target Group | [5 empty] | done
9 | Configure Certificate for AWS ACM | [5 empty] | done
10 | Create WAF Rule | [5 empty] | done
11 | Create Security Group | [5 empty] | done
12 | Setup SubnetGroup for Aurora | [5 empty] | done
13 | Provisioning Aurora Postgresql | [5 empty] | done
14 | Use existing Setup IAM Role (Manually Copy ARN in cloudformation template) | [5 empty] | done
Create Autoscalling
15 | Create Daily Backup | [5 empty] | on progress
Manual Provisioning
17 | Database Migration and Configuration
18 | Create 2 EFS Data & Code
19 | Configure EFS Policies on EFS
20 | TEDS ASP Data Migration to EFS testing
21 | Create 2 EC2 Master (APPS, Cron)
22 | Install CloudWatch and SSM Agent
23 | Mounting EFS to EC2
24 | Deploy Application
25 | Create Golden AMI
26 | ALB listerner rules Configuration
Configure AWS Infra 2nd Launch
28 | Configure EC2 for Auto Scaling Group AMI(Golden Image)
29 | Create AMI if Auto Scaling Group is used
Manual Provisioning Moniitoring
31 | Create CloudWatch Dashboard
Review AWS Environment Configuration
33 | Functional Testing
34 | Create Report & Documentation

## Mapping Folder
Existing |  | New | Status | Todo: | Permission
/opt/odoo/teds-git/IN |  | /opt/asp_teds_data/data_share/IN | Done | Konfirmasi Pak Joen Cron untuk masukan file MFT ke Folder IN | odoo
/opt/odoo/teds-git/ARCIN |  | /opt/asp_teds_data/data_share/ARCIN | Done | Konfirmasi Pak Joen Cron untuk masukan file MFT ke Folder IN | odoo
/opt/odoo/teds-git/PROC | /data/data_share/PROC | /opt/asp_teds_data/data_share/PROC | Done | Konfirmasi Pak Joen Cron untuk masukan file MFT ke Folder IN | odoo
/opt/odoo/teds-git/ERROR | /data/data_share/ERROR | /opt/asp_teds_data/data_share/ERROR | Done | Konfirmasi Pak Joen Cron untuk masukan file MFT ke Folder IN | odoo
/opt/odoo/teds-git/EPICOR | /data/data_share/EPICOR/ | /opt/asp_teds_data/data_share/EPICOR | Done | Make Sure Epicor Terkirim | root
/opt/odoo/teds-git/EPICOR_DONE |  | /opt/asp_teds_data/data_share/EPICOR_DONE | Done | Make Sure Epicor Terkirim | root
/opt/odoo/teds-git/parts_daily | /data/data_share/parts_daily/ | /opt/asp_teds_data/data_share/parts_daily/ | Done | - | root
/opt/odoo/teds-git/parts_daily_retail | /data/data_share/parts_daily_retail/ | /opt/asp_teds_data/data_share/parts_daily_retail/ | Done | - | root
/opt/odoo/data_store/MFT/MFT_DONE |  | /opt/asp_teds_data/data_share/MFT/MFT_DONE | Done | - | odoo
| /data/data_share/ANAPLAN/ | /opt/asp_teds_data/data_share/ANAPLAN/ | Done
| /data/data_share/backup_log_api | /opt/asp_teds_data/data_share/backup_log_api | Done
| /data/data_share/prop_files | /opt/asp_teds_data/data_share/prop_files | Done
| /data/data_share/invoice_wa | /opt/asp_teds_data/data_share/invoice_wa | Done
/opt/asp_teds_data/data_share/static

## Sheet1
Concern | PIC
IP Static dari portal ke TEDS ASP | MBN
API : TEDS dan DMS ke Portal | JAN
API ke AHM, JNE, Finco, TOB | JAN
MFT AHM ke TEDS/DMS | MBN | user sendiri buat MFT TEDS
VPN ke server | MBN
Code masih ada pakai IP | JAN
Leasing api | JAN
EPICORE makesure pakai atau nggak | JAN
Ckslt fungsionalitas menu TEDS ASP | UAN

## Sheet2
activity | status
Launch Master AMI Web APP From Golden Image SATU | done
Launch Master AMI Cron From Golden Image SATU | done
Update & upgrade server | done
Create logging teds-asp-server.log | done
Settings CW agent | done
Check mounting kedua server | done
fs-05435bd418f534e0f /opt/dht_satu_data/ efs _netdev,noresvport,tls,accesspoint=fsap-0e822145b8694737a 0 0
fs-04f99a2e205500020 /opt/dht_satu_code/ efs _netdev,noresvport,tls,accesspoint=fsap-052057b66cc3da4cf 0 0
fs-04f99a2e205500020 /opt/odoo/file_store/filestore/ efs _netdev,noresvport,tls,accesspoint=fsap-052057b66cc3da4cf 0 0
fs-05a2d0dc015a1dcb8 /opt/asp_teds_data/ efs _netdev,noresvport,tls,accesspoint=fsap-0a7391a96d00e2cdb 0 0
fs-097f1a253f77120bb /opt/asp_teds_code/ efs _netdev,noresvport,tls,accesspoint=fsap-045962fd10f8e387c 0 0
fs-097f1a253f77120bb /opt/odoo/file_store/filestore/ efs _netdev,noresvport,tls,accesspoint=fsap-045962fd10f8e387c 0 0
Create user for mft | done
Restore Database from prod | done
Copy Datashare to efs | done
Launch application | done
Create service for teds-asp.service | done

## rundown
Rundown Actities Migration
|  |  |  | PLAN |  |  |  | ACTUAL
No | Activity | Details | PIC | Date | Start | End | Duration | Date | Start | End | Duration | Remark | Status
1 | Hoki
| Stop service hoki |  | M. Bella BN | 2021-11-13 18:00 | 18:30 | 18:35 | 0:05
| Change Domain Hoki in DNS & Accessvenom |  | M. Bella BN | 2021-11-13 18:00 | 18:35 | 18:40 | 0:05
| Backup Database Hoki |  | M. Bella BN | 2023-04-23 | 18:40 | 23:00 | 4:20
| Backup & rsync static file hoki |  | M. Bella BN | 2021-11-13 18:00 | 18:40 | 22:00 | 3:20
| Send Database Hoki Stagging |  | M. Bella BN | 2021-11-13 18:00 | 23:00 | 1:00 | -0.91667
| Send Database Hoki on Stagging to S3 |  | M. Bella BN | 2021-11-13 18:00 | 1:00 | 4:00 | 3:00
| Send Database Hoki on s3 to stagging restore |  | M. Bella BN | 2021-11-13 18:00 | 4:00 | 5:00 | 1:00
| Restore Database HoKi on ec2 |  | M. Bella BN | 2021-11-14 18:00 | 5:00 | 10:00 | 5:00
| Start service HoKi |  | M. Bella BN | 2021-11-14 18:00 | 10:00 | 10:05 | 0:05
| Upgrade module Base |  | M. Bella BN | 2021-11-14 18:00 | 10:05 | 10:30 | 0:25
| Checking static file on transaction |  | Nagara | 2021-11-14 18:00 | 10:30 | 10:40 | 0:10
| Change Static File Config via web |  | Nagara | 2021-11-14 18:00 | 10:40 | 10:45 | 0:05
| Change Path Send file MFT Linux |  | M. Bella BN | 2021-11-14 18:00 | 10:45 | 10:50
Change dashboard hoki dashboard.honda-ku.com